# HIGH-LEVEL CARF ACCREDITATION CONSULTING WORKFLOW

Lead → Qualification → Discovery → Proposal → Engagement Letter

→ Readiness Assessment → Gap Analysis → Action Plan

→ Policy & Procedure Development → Staff Training

→ Implementation Support → Mock Survey

→ Corrective Action → Survey Support

→ Post-Survey Follow-Up → Continuous Compliance Plan

# PHASE 1: PRE-ENGAGEMENT & SCOPING

## 1️⃣    Lead & Initial Inquiry

Owner: Managing Consultant / Partner

Capture:

- Programs seeking accreditation (OMHC, PRP, IOP/OP)

- Initial accreditation or reaccreditation?

- Current CARF status?

- State requirements?

- Timeline for survey?

- Number of sites?

- Staff size?

- EMR system?

- Prior deficiencies?

Immediate Red Flags:

- Survey already scheduled within 60 days

- No clinical leadership in place

- No QI structures

- High staff turnover

- Prior denial

## 2️⃣   Qualification & Feasibility Review

Assess:

- Timeline realistic?

- Agency leadership committed?

- Budget aligned with scope?

- Capacity for implementation?

Deliverable:

- Internal Risk Assessment Memo

## 3️⃣   Discovery & Scoping Call

Clarify:

- Programs to be accredited

- Applicable CARF standards manual

- Scope of consulting (full build vs gap remediation)

- Onsite vs virtual support

- Expected survey window

Define:

- Consulting model (retainer vs milestone-based)

## 4️⃣   Proposal & Engagement Letter

Include:

- Scope of services

- Deliverables

- Timeline

- Client responsibilities

- Confidentiality

- Fee schedule

- Payment terms

- Non-guarantee clause (important)

Require:
 Signed engagement letter
 Initial retainer

# PHASE 2: READINESS ASSESSMENT

## 5️⃣   Document Request & Data Collection

Request:

### Governance

- Organizational chart

- Board bylaws

- Meeting minutes

### Clinical

- Policies & procedures

- Intake forms

- Treatment plans

- Progress note templates

- Discharge summaries

### HR

- Personnel files

- Licenses

- Job descriptions

- Supervision logs

### Quality Improvement

- QI plan

- KPI dashboard

- Incident reports

- Risk management plan

### Compliance

- HIPAA policies

- Grievance procedures

- Corporate compliance plan

## 6️⃣   Readiness Assessment Review

Consultant reviews:

- Policies vs CARF standards

- Clinical documentation samples

- HR compliance

- Governance structure

- Performance improvement processes

Deliverable:
Readiness Scorecard
Preliminary Findings Report

# PHASE 3: GAP ANALYSIS & ACTION PLAN

## 7️⃣   Formal Gap Analysis

Map agency operations against:

- CARF General Standards

- Behavioral Health Standards

- Program-specific standards (OMHC, PRP, IOP/OP)

Categorize gaps:

| Level | Description |
| --- | --- |
| Critical | Would result in denial |
| Major | High risk |
| Moderate | Needs improvement |
| Minor | Documentation fix |

Deliverable:
Detailed Gap Analysis Report

## 8️⃣   Corrective Action Plan (CAP)

Create:

- Task list

- Responsible party

- Deadline

- Required documentation

- Training requirements

Deliverable:

90–180 Day Readiness Plan

# PHASE 4: POLICY & INFRASTRUCTURE DEVELOPMENT

## 9️⃣   Policy & Procedure Development

Develop or revise:

- Governance policies

- Clinical documentation standards

- Individualized treatment planning

- Incident reporting

- Medication management

- Risk management

- Cultural competency

- Performance improvement

- Accessibility & non-discrimination

- Infection control (if applicable)

Deliverable:
CARF-Compliant Policy Manual

## Program-Specific Alignment

### OMHC Focus:

- Medical necessity documentation

- Psychiatric evaluation standards

- Treatment plan reviews

### PRP Focus:

- Rehabilitation goals

- Community integration documentation

- Service authorization compliance

### IOP/OP Focus:

- Group documentation

- Clinical hours compliance

- Level-of-care criteria

- Transition planning

# PHASE 5: TRAINING & IMPLEMENTATION

## 1️⃣1️⃣   Leadership Training

Train:

- Executive team

- Clinical supervisors

- Compliance officer

Topics:

- CARF philosophy

- Person-centered care

- Evidence-based practices

- QI expectations

- Documentation standards

## 1️⃣2️⃣   Staff Training

Conduct:

- Clinical documentation training

- Treatment planning standards

- Progress note compliance

- Incident reporting procedures

- Cultural competency

Deliverables:
Attendance logs
Training materials
 Sign-in sheets

# PHASE 6: IMPLEMENTATION SUPPORT

## 1️⃣3️⃣    Documentation Audits

Sample:

- 10–20 charts per program

Evaluate:

- Timeliness

- Clinical appropriateness

- Treatment plan alignment

- Measurable goals

- Progress linkage

Deliver:
Audit Findings Report
Corrective Recommendations

## 1️⃣4️⃣    Quality Improvement System Setup

Establish:

- KPI dashboard

- Performance metrics

- Quarterly review structure

- Incident trend analysis

- Consumer satisfaction surveys

Deliver:
QI Framework Toolkit

# PHASE 7: MOCK SURVEY

## 1️⃣5️⃣   Full Mock Survey (Onsite or Virtual)

Simulate:

- Leadership interviews

- Staff interviews

- Consumer interviews

- Documentation review

- Environment review

Deliver:
Mock Survey Report
Deficiency Risk List

# PHASE 8: FINAL PREPARATION

## 1️⃣6️⃣   Corrective Action Implementation

Address:

- Remaining deficiencies

- Missing policies

- Incomplete documentation

- Staff retraining

## 1️⃣7️⃣    Survey Logistics Preparation

Prepare:

- Survey binder

- Document access

- Interview schedule

- Staff briefing session

- Survey day flow plan

Deliver:
Survey Readiness Binder

# PHASE 9: LIVE SURVEY SUPPORT

Consultant provides:

- On-call support

- Response coaching

- Clarification assistance

- Immediate corrective drafting (if needed)

# PHASE 10: POST-SURVEY SUPPORT

## 1️⃣8️⃣    Review Findings

If findings issued:

- Develop corrective action response

- Draft formal response

- Submit within CARF timeline

## 1️⃣9️⃣   Continuous Compliance Plan

Establish:

- Ongoing quarterly audits

- Annual policy review cycle

- KPI review calendar

- Staff re-training schedule

Deliver:
12-Month Compliance Maintenance Plan

# RESPONSIBILITY MODEL (CONSULTING FIRM)

| Role | Responsibility |
| --- | --- |
| Managing Consultant | Scope, oversight |
| Senior Consultant | Gap analysis, mock survey |
| Clinical SME | Documentation review |
| Compliance Specialist | Policy drafting |
| Project Coordinator | Tracking & scheduling |
| Admin | Document management |

# TYPICAL TIMELINE

| Engagement Type | Timeline |
| --- | --- |
| Full Accreditation Build | 6–9 months |
| Gap Remediation | 3–6 months |
| Mock Survey Only | 4–6 weeks |

RISK CONTROL POINTS

Critical controls:

Scope clearly defined
Non-guarantee clause in contract
Survey window confirmed
All recommendations documented
Client responsible for implementation
No clinical advice beyond licensure scope

# LIFECYCLE MODEL

Assessment

↓

Gap Analysis

↓

Infrastructure Build

↓

Training

↓

Mock Survey

↓

Live Survey Support

↓

Corrective Action

↓

Ongoing Compliance Retainer